## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2235-swen-261-8-h Duck Investments
Testing Team Name | 2235-swen-261-6-f Julian and the Maurices

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed) | date; comments (required if test failed) | date; comments (required if test failed) | Tester #2 | Tester #3 | date; comments (required if test failed) | Tester #1
AS a Developer I WANT to submit a request to get the entire cupboard SO THAT I have access to all of the needs for the organization. | GIVEN I submit a request for the inventory WHEN products exist in the inventory THEN the system updates that need and returns 200 (OK) | Pass | A.L; 3/16/2024 | Pass | A.L; 4/2/2024
| GIVEN I submit a request for the inventory WHEN no products exist in the inventory THEN does not update anything and returns a status code of 200 (OK) | Pass | A.L; 3/16/2024 | Pass | A.L; 4/2/2024
As a Admin want to submit a request to delete a single need SO THAT it is no longer in the cupboard | Given the requested need exists, when the user requests to delete a need, then the need will be deleted from the cupboard. | Pass | A.L; 3/16/2024 | Pass | A.L; 4/2/2024 |  |  | Pass | Pass
| Given the requested need does not exist, when the user requests to delete a need, then a 404 error is given. | Pass | A.L; 3/16/2024 | Pass | A.L; 4/2/2024 | When nothing is selected and Remove is clicked on, it says on the top right that "Nonewas deleted" SN 4/2/24 |  | Fail | Pass | I was getting a different result than tester #1. Possibly on a different version or branch of the project. Nothing was happening for me.
AS a user I WANT to submit a request to get a single need SO THAT I can access the cost, quantity and type. | Given that the requested need exists, when a user requests a need then display the need and its information. | Pass | A.L; 3/16/2024 | Pass | A.L; 4/2/2024
| Given that the requested need does not exist, a 404 error is given. | Pass | A.L; 3/16/2024 | Pass | A.L; 4/2/2024
AS a Admin I WANT to submit a request to create a new need (name [unique], cost, quantity, type) SO THAT it is added to the cupboard. | GIVEN I submit a need object WHEN no need with the given name exists THEN the system should create the need, add it to the cupboard, save to the persistent storage, and return the need object and a status code of 201 (CREATED) | Pass | A.L; 3/16/2024 | Pass | A.L; 4/2/2024 | Even if the name is only whitespace then the need is successfully created. SN 4/2/24 |  | Fail | Pass |  | Pass
| GIVEN I submit a need object WHEN a need with the given name already exists THEN the system should return a status code of 409 (CONFLICT) | Pass | A.L; 3/16/2024 | Pass | A.L; 4/2/2024 |  |  |  | Pass |  | Pass
AS A Admin I WANT to submit a request to get the cupboard SO THAT I can update needs in the cupboard. | GIVEN I submit a request for the inventory WHEN products exist in the inventory THEN the system should return a list of products and a status code of 200 (OK) | Pass | A.L; 3/16/2024 | Pass | A.L; 4/2/2024; For both edit and add I tested negative and decimal numbers, names with whitespace, blank words, duplicate words, and duplicate names with whitespace. Likewise I tested undefined values. | [5 empty] | Pass
| GIVEN I submit a request for the inventory WHEN no products exist in the inventory THEN the system should return an empty list of products and a status code of 200 (OK) | Pass | A.L; 3/16/2024 | Pass | A.L; 4/2/2024 | [5 empty] | Pass
AS a Developer I WANT to submit a request to get the the needs in the cupboard whose name contains the given text, SO THAT I have access to only that subset of needs. | GIVEN the subset exists, WHEN the user requests for the subset THEN the subset of the cupboard gets displayed to the user and status code of 200 (OK) | Pass | K.B; 3/18/2024 | Pass | A.L; 4/2/2024
| GIVEN the subset does not exist WHEN the user requests for the subset THEN the the user is informed that it does not exist with a status of 200 (OK) | Pass | K.B; 3/18/2024 | Pass | A.L; 4/2/2024
As a U-fund Manager, I want to be able to able to add, remove, and edit data in a cupboard so that the needs are not static, but can be changed. | **Given** a cupboard item exists **when** I request for a cupboard to be deleted, **then** expect the cupboard item to be removed and a return code of OK | Pass | K.B; 3/18/2024 | Pass | A.B; 4/2/2024 |  |  |  | Pass |  | Pass
| **Given** a cupboard item exist **when** I request an edit on that item, **then** I expect the cupboard item to change and to return a code of OK | Pass | K.B; 3/18/2024 | Pass | A.B; 4/2/2024 |  |  |  | Pass |  | Pass
| **Given** a cupboard item does not exists, **when** I request to add a need, **then** I expect the cupboard to have that item added and return a code of OK | Pass | K.B; 3/18/2024 | Pass | A.B; 4/2/2024 |  |  |  | Pass |  | Pass
As a User I want to get my profile so that I can access the needs in my funding basket after logging in. | **Given** a user exists **when** a helper enters the username of the user **then** the helper will gain access to that user profile | Pass | K.B; 3/18/2024 | Pass | A.L; 4/2/2024 |  |  |  | Pass |  | Pass
| **Given** there exists a user admin **when** an administrator enters the username 'admin' **then** the administrator will gain access to a user profile with special permissions | Pass | K.B; 3/18/2024 | Pass | A.L; 4/2/2024 |  |  |  | Pass |  | Pass
As a developer I want to change attributes of the user profile so that actions taken by that user can be saved. | **Given** a user exists **when** that user makes changes to their funding basket **then** the user profile will update to reflect those changes. | Pass | K.B; 3/18/2024 | Pass | A.L; 4/2/2024
As a user I want to be able to add and remove needs from my funding basket. | Given the requested need exists in the funding basket, when an *add to basket* request is submitted, then the need will be added to the funding basket | Pass | K.B; 3/18/2024 | Pass | K.B; 4/2/2024 |  |  |  | Pass |  | Pass
| Give the requested need exists in the funding basket, when a *remove from basket* request is submitted, then the need will be removed from the funding basket | Pass | K.B; 3/18/2024 | Pass | K.B; 4/2/2024 |  |  |  | Pass |  | Pass
| Give the requested need does not exist in the funding basket, when a *remove from basket* request is submitted, then a 404 error will be given. | Pass | K.B; 3/18/2024 | Pass | K.B; 4/2/2024 unreachable fail case |  |  |  | Pass | User can only attempt to remove need if it exists in the funding basket. Technically a pass. | Pass
As a donor I want to see the needs in my funding basket from previous sessions so that I can come back to the page without losing progress. | Given that I try to access my funding basket, my progress should be saved to a file so that my progress is not lost. | Pass | K.B; 3/18/2024 | Pass | A.B; 4/2/2024 |  |  |  | Pass |  | Pass
| Given that I am a new user, when I access my funding basket, then I should see a brand new funding basket | Pass | K.B; 3/18/2024; | Pass | A.B; 4/2/2024 |  |  |  | Pass |  | Pass
As a donor I want to move my funding basket to the checkout so that I can purchase my selected needs. | **Given** the basket is empty **when** a helper tries to checkout **then** nothing happens. |  |  | Pass | A.B; 4/2/2024 |  |  |  | Pass |  | Fail
| Given the basket has needs when a helper tries to checkout, then the items are removed from the basket and the cupboard |  |  | Pass | A.B; 4/2/2024 |  |  |  | Pass
As a new user I want to create a new profile so that I can use the site and store my progress. | **Given** a user profile does not exist **when** a user logs in with a new username **then** a new user profile will be created. | Pass | A.B; 3/18/2024; |  | functionality removed |  | When I attempted to login with a new username I had to sign up first 4/2/24 When I try to create a user with a username that is already in use, I get a success message but the new account is not actually created. |  | Fail | Usernames/passwords can be whitespace. SN 4/2/24 | Fail
| **Given** a user tries to create a new account **when** they dont enter a username **then** an account will not be created and the user gets notified to enter a username |  |  | Pass | A.B; 4/2/2024 |  | You can enter white space as both a username and password and still successfully make an account JA 4/2/24 |  |  |  | Fail
| **Given** a user tries to create a new account **when** they dont enter a password **then** an account will not be created and the user gets notified to enter a password |  |  | Pass | A.B; 4/2/2024 | [5 empty] | Pass
| **Given** a user is on the login page **when** they request to go to the sign up page **then** they should be redirected to the signup screen |  |  | Pass | A.B; 4/2/2024 | [5 empty] | Pass
| **Given** a user is on the sign up page **when** they request to go to the login page **then** they should be redirected to the login screen |  |  | Pass | A.B; 4/2/2024 | [5 empty] | Pass
As a user I want to login so I can access my account. | **Given** a user provides a valid username and password **when** the user tries to log in **then** they are logged in. | Pass | A.B; 3/18/2024; | Pass | K.B; 4/2/2024 | [5 empty] | Pass
| Given a user does not have the username admin when the navigate to the cupboard then they should NOT have permission to edit the cupboard/needs | Pass | A.B; 3/18/2024; | Pass | K.B; 4/2/2024 routed back to login | [5 empty] | Pass
| **Given** a user enters username admin **when** they navigate to the cupboard **then** they should have permission to edit the cupboard/needs | Pass | A.B; 3/18/2024; | Pass | K.B; 4/2/2024 | [5 empty] | Pass
| Given a user provides an invalid username or password when the user tries to log in then they are shown an error message. | Pass | A.B; 3/18/2024; | Pass | K.B; 4/2/2024 | [5 empty] | Pass
As a donor I want to put a need into my funding basket so that I can fulfill that need. | Given a need does not exist when a user selects the need then the server will display an error message (status code 404) | Pass | A.B; 3/18/2024; | Pass | K.B; 4/2/2024 unreachable fail case |  | I attempted to delete a need from the admin side, the need still showed up on the donor side, Accepted the request JA 4/2/24 |  |  |  | Fail
| **Given** a need exists **when** the user selects that need **then** the need will be added to the user's funding basket (status code 200) | Pass | A.B; 3/18/2024; | Pass | K.B; 4/2/2024 |  |  |  | Pass | This works but the needs themselves are presented as buttons, even though nothing happens when you click on them. SN 4/2/24 | Pass
As a donor I want to remove a need from my Funding Basket so that I can curate a funding basket that only has needs I want to donate to. | **Given** a helper has a need in their funding basket **when** they make a request to remove the item **then** the item is removed from their basket. | Pass | K.B; 3/18/2024; | Pass | K.B; 4/2/2024 | [5 empty] | Pass
| **Given** the need is not in the funding basket **when** I want to remove it then the **need** is not deleted and a NOT_FOUND code is returned | Pass | K.B; 3/18/2024; | Pass | K.B; 4/2/2024 unreachable fail case |  | You can still remove needs even if they dont exist JA 4/2/24 |  |  |  | Fail
As an Administrator I want to create need bundles so that needs can be grouped into various categories (time, material, monetary, priority, etc.). | **Given** a bundle does not exist **when** I add a bundle **then** I expect the collection of bundles to now feature it and return OK |  |  | Pass | K.B; 4/2/2024
| **Given** a bundle already exist **when** I add a bundle **then** I expect the system to not add it and return EXPECTATION_FAILED |  |  | Pass | K.B; 4/2/2024
As a donor I want to add a bundle to my funding basket so that I can donate to all the needs in the bundle at once. | **Given** a bundle exists within the cupboard **when** a user selects a bundle **then** the bundle is added to the user's funding basket. (return status code 200) |  |  | Pass | K.B; 4/2/2024 adds all needs from the bundle
| **Given** a bundle does not exist within the cupboard, **when** a user selects a nonexistent bundle **then** do nothing and return a status code 404 |  |  | Pass | K.B; 4/2/2024 unreachable case
AS a Manager I WANT to submit a request to edit a Bundle (name [unique], cost, quantity, type) SO THAT its content gets changed. | GIVEN I submit a **bundle edit** request WHEN a **bundle** with the given name already exists THEN the system would change the content of the bundle and return a status code of 204 (NO CONTENT) |  |  | Pass | K.B; 4/2/2024
| GIVEN I submit a **bundle edit **request WHEN a **bundle** with the given name does not exist THEN the system should return a status code of 404 (NOT FOUND) |  |  | Pass | K.B; 4/2/2024
As a user I want to be notified about changes to the cupboard so that I can adjust my funding basket accordingly. | **Given** an admin makes a change to the cupboard **when** any user is logged in **then** they will be informed of the most recent change |  |  | Pass | K.B; 4/2/2024 | [5 empty] | Pass
| **Given** A user has a certain need in their funding basket **when** another user contributes to that certain need and reaches the goal **then** the user will be notified that any further donation is surplus. |  |  | Pass | A.B; 4/2/2024 | [5 empty] | Pass
| **Given** any type of user is logged in **when** they request to view notification history **then** they will see the list of all notifications that have been made. |  |  | Pass | A.B; 4/2/2024 | [5 empty] | Pass
As a Admin I want to be able to see the donated quantity of each need so that know how much of each need is promised. | **Given** An admin is logged in **when** they request to view the need tracker **then** a list of each need and the donated quantity is displayed . |  |  | Pass | K.B; 4/2/2024 displays surplus in admin cupboard
As a User I want to save my login information so that I don't have to log back in every time the page is reloaded. | Given I am logged in when I reload the page then I expect be auto logged back in | Pass | A.L; 4/2/2024 | Pass | K.B; 4/2/2024 | [5 empty] | Pass
| Given I am not logged in when I reload the page then I expect to be sent back to the log in page | Pass | A.L; 4/2/2024 | Pass | A.L; 4/3/2024; | [5 empty] | Pass
As a User I want to view my profile details so that I can change my username/password or delete my profile. | **Given** A user is logged in **when** they request to view their profile **then** their profile details should be displayed. |  |  | Pass | U.N.; 4/2/2024 | [5 empty] | Pass
| **Given** A user exists **when** a user requests to change their profile details **then** their profile should update to reflect their changes |  |  | Pass | U.N.; 4/2/2024
| **Given** A user is logged in **when** they request to delete their profile **then** their profile should be deleted and they will be navigated back to the login page. |  |  | Pass | U.N.; 4/2/2024
As a user I want to have a wallet so that I can pay for the needs I’m contributing to. | **Given** a user is logged in **when** They access their profile **then** the amount of money in their wallet is displayed. |  |  | Pass | A.B; 4/2/2024 | [5 empty] | Pass
| **Given** a user is logged in **when** They request to add a specific amount of money to their wallet **then** that amount is added to their wallet. |  |  | Pass | A.B; 4/2/2024 | [5 empty] | Pass
| **Given** a user is in checkout **when** They request to check out their needs **then** the total they have to pay is removed from their wallet. |  |  | Pass | A.B; 4/2/2024 | [5 empty] | Pass
| **Given** a user is checking out **when** the total for their needs is more than what they have in their wallet **then** the transaction is cancelled and the user is notified that they don't have enough money. |  |  | Pass | A.B; 4/2/2024 | [5 empty] | Pass